## Sheet1
STEPS | FUNCTIONS | 1 week | 2 week | 3 week | 4 week | 5 week | 6 week | 7 week | 8 week | 9 week | 10 week | 11 week | 12 week | 13 week | 14 week | 15 week | 16 week | 17 week | 18 week | 19 week | 20 week | 21 week | 22 week | 23 week | 24 week | 25 week | 26 week | 27 week | 28 week | 29 week | 30 week | 31 week | 32 week | 33 week | 34 week | 35 week | 36 week | 37 week | 38 week | 39 week | 40 week
STAGE 1
MARKET RESEARCH AND TECHNICAL FEASIBILITY
1 | Develop Commercialization Time Line | bar: 1 week to 2 week
2 | Assess competition and market share | bar: 1 week to 2 week; 6 week to 7 week
3 | Assess Customer Needs and Preferences | bar: 2 week to 3 week
4 | Identify Target market | bar: 2 week to 3 week
5 | Develop product mock up | bar: 3 week to 9 week
6 | Hold focus groups | bar: 1 week to 2 week
7 | Develop product definintion | bar: 3 week to 4 week
8 | Assess technical feasibility of project | bar: 6 week to 8 week
9 | Assess mgmt capabilities for project | bar: 4 week to 8 week
10 | Recruit Project Team | bar: 2 week to 7 week
11 | Determine project costs | bar: 9 week to 10 week
12 | Assess regulatory environment etc. | bar: 4 week to 6 week
13 | Build business case | bar: 8 week to 9 week
14 | Obtain initial round of financing | bar: 1 week to 9 week
15 | Other tasks as required:
STAGE 2
PRODUCT DEVELOPMENT AND TESTING
14 | Detail the product development plan | bar: 9 week
15 | Develop the prototype | bar: 9 week to 16 week
16 | Get end-user feedback | bar: 12 week to 17 week
17 | Refine product based on feedback | bar: 12 week to 20 week
18 | Carry out in-house testing | bar: 16 week to 20 week
19 | Do Field trials | bar: 16 week to 20 week
20 | Obtain regulatory appovals | bar: 16 week to 20 week
21 | Apply for patents | bar: 16 week to 20 week
22 | Update business plan | bar: 16 week to 20 week
23 | Develop marketing plan | bar: 1 week to 19 week
24 | Secure final stage financing | bar: 10 week to 18 week
25 | Other tasks as required: | bar: 19 week to 21 week
STAGE 3
26 | PRODUCTION & MARKET LAUNCH
27 | Develop Production Plan | bar: 22 week to 28 week
28 | Purchase and set up equipment | bar: 22 week to 28 week
29 | Train Production Staff | bar: 22 week to 28 week
30 | Conduct trial production run | bar: 28 week to 29 week
31 | Quality Assurance Plan | bar: 24 week to 28 week
32 | Consider R&D function | bar: 26 week to 30 week
33 | Establish Accounting System | bar: 11 week to 30 week
34 | Develop Management Reports | bar: 28 week to 33 week
35 | Obtain & Equip Administration Facility | bar: 28 week to 33 week
36 | Develop Administrative Systems | bar: 28 week to 33 week
37 | Develop Distribution Systems | bar: 20 week to 25 week
38 | Develop Packaging Designs | bar: 20 week to 25 week
39 | Develop Logistical Systems | bar: 11 week to 30 week
40 | Establish Prices & Terms of Sale | bar: 11 week to 30 week
41 | Develop the New Product Brand Program | bar: 11 week to 30 week
42 | Develop Trade Names & Trademarks | bar: 22 week to 30 week
43 | Develop Marketing Messages | bar: 22 week to 30 week
44 | Develop the Graphics Identification | bar: 22 week to 30 week
45 | Develop the Publicity Program | bar: 22 week to 30 week
46 | Develop the Advertising Program | bar: 17 week to 28 week
47 | Develop the Trade Show Program | bar: 17 week to 28 week
48 | Develop the Company Brochure | bar: 17 week to 28 week
49 | Develop the Product Brochure | bar: 17 week to 28 week
50 | Develop the Customer Relations Program
51 | Develop the Technical Support Program | bar: 26 week to 35 week
52 | Develop the User Training Program | bar: 26 week to 35 week
53 | Develop the Supplies & Parts Program | bar: 26 week to 35 week
54 | Develop the Internet Site | bar: 26 week to 35 week
55 | Set up Board of Directors | bar: 4 week to 17 week
56 | Establish Mentors and business advisors | bar: 16 week to 38 week
57 | Establish Human Resource Strategy | bar: 16 week to 38 week
58 | Production Launch | bar: 16 week to 38 week
59 | Market Launch | bar: 39 week to 40 week
60 | Other tasks as required: | bar: 39 week to 40 week
PROJECT REVIEW